## C39
Table C39 Size Estimating Template (p. 683)
Student | Greg Vannoni |  |  |  | Date |  | 2010-03-05
Instructor | G. Booker |  |  |  | Program # |  | 6B
BASE PROGRAM |  |  |  |  | Estimate |  | Actual
BASE SIZE (B) => => => => => => => => |  |  |  |  | 324 |  | 324
LOC DELETED (D) => => => => => => => => |  |  |  |  | 3
LOC MODIFIED (M) => => => => => => => => |  |  |  |  | 5
OBJECT LOC
BASE ADDITIONS: |  | TYPE | METHODS | REL. SIZE | Estimate LOC |  | Actual LOC
Add regression calculations to Main |  | C | 1 | M | 5
Add functionality to convert Jlist to ArrayList<ArrayList<String>> |  | D | 1 | M | 5
Add regression calculation output to GUI |  | T | 1 | M | 5
TOTAL BASE ADDITIONS (BA) => => => => => |  |  |  |  | 15
NEW OBJECTS: |  | TYPE | METHODS | REL. SIZE | Estimate LOC | (New Reuse*) | Actual LOC
RegressionCalculation |  | C | 8 | L | 16
TOTAL NEW OBJECTS (NO) => => => => => => => |  |  |  |  | 16
REUSED OBJECTS |  | TYPE | METHODS | REL. SIZE | Estimate LOC |  | Actual LOC
MainFrame - getJListAsArrayList |  | D | 1 | M | 5
REUSED TOTAL (R) => => => => => => => => => |  |  |  |  | 5 |  | 0
[5 empty] | SIZE |  | TIME
Estimated Object LOC (E) = BA + NO + M: |  |  |  |  | 36 |  | 36
Regression Parameter: |  | b1 |  |  | 1.2303 |  | 5.7693
Regression Parameter: |  | b0 |  |  | -0.45418 |  | 32.472
Estimated New and Changed LOC (N) = b0 + b1*E: |  |  |  |  | 43.8355 |  |  | (N) should feed into total new and changed code in C55
Estimated Total LOC T = N + B - D - M + R: |  |  |  |  | 357
Estimated Total New Reused (sum of * LOC): |  |  |  |  | 16
Estimated Total Development Time (hrs) = b0 + b1*E | [6 empty] | 240.1682 | Should feed into C47, C49, C55 as total planned time
Prediction Range: |  |  |  |  | 24.3623 |  | 175.9513
Upper Prediction Interval: |  |  |  |  | 68.1978 |  | 416.1195
Lower Prediction Interval: |  |  |  |  | 19.4732 |  | 64.2169
Prediction Interval Percent: |  |  |  |  | 70% |  | 70% | PIP should be equal for both regressions

## Proxy
Assignment 1B | Size (LOC) | Ln(Size) | (Ln(Size)-AveSize)^2 | Type
Main | 32 | 3.4657 | 3.1227 | control
MainFrame | 1 | 0 | 2.8853
displayError | 2 | 0.69315 | 1.011
displayWarning | 2 | 0.69315 | 1.011
displayArrayList | 3 | 1.0986 | 0.36 |  | average of logs | 1.6986
getJListPane | 3 | 1.0986 | 0.36 |  | sum of column D | 151.8737
getReadWriteMode | 6 | 1.7918 | 0.0086762 |  | variance | 1.1086
getSingleNumberInput | 11 | 2.3979 | 0.489 |  | std dev | 1.0529
getNumbersInput | 6 | 1.7918 | 0.0086762
getQuantityOfNumbers | 11 | 2.3979 | 0.489
getFileLocation | 12 | 2.4849 | 0.61826
initializeAndDisplay | 25 | 3.2189 | 2.3112
MyFileReader | 4 | 1.3863 | 0.097543
getFileContents | 6 | 1.7918 | 0.0086762
MyFileWriter | 4 | 1.3863 | 0.097543
setFileContents | 5 | 1.6094 | 0.0079522
FileModeType | 5 | 1.6094 | 0.0079522
toString | 1 | 0 | 2.8853
Assignment 2A
Main | 41 | 3.7136 | 4.0601
MainFrame | 1 | 0 | 2.8853
displayError | 2 | 0.69315 | 1.011
displayArrayList | 3 | 1.0986 | 0.36 |  |  | LN(midpoint) | Midpoints (LOC)
getJListScrollPane | 4 | 1.3863 | 0.097543 |  | very small = ave - 2*std dev | -0.40716 | 0.66554
getFileLocation | 12 | 2.4849 | 0.61826 |  | small = ave - std dev | 0.64573 | 1.9074
initializeAndDisplay | 26 | 3.2581 | 2.432 |  | medium = average | 1.6986 | 5.4664
MyFileReader | 4 | 1.3863 | 0.097543 |  | large = ave + std dev | 2.7515 | 15.6661
getFileContents | 6 | 1.7918 | 0.0086762 |  | extra large = ave + 2*std dev | 3.8044 | 44.8976
MyFileWriter | 4 | 1.3863 | 0.097543
setFileContents | 5 | 1.6094 | 0.0079522
CountingStandard | 10 | 2.3026 | 0.36478
isLogicalLineOfCode | 16 | 2.7726 | 1.1534
LOCCounter | 2 | 0.69315 | 1.011
getLogicalVisualLOC | 6 | 1.7918 | 0.0086762
countLogicalLOC | 6 | 1.7918 | 0.0086762
countPhysicalLOC | 2 | 0.69315 | 1.011
Assignment 2B
Main | 46 | 3.8286 | 4.537
MainFrame | 1 | 0 | 2.8853
displayError | 2 | 0.69315 | 1.011
displayWarning | 2 | 0.69315 | 1.011
displayArrayList | 3 | 1.0986 | 0.36
getJListAsArray | 4 | 1.3863 | 0.097543
displaySingleString | 4 | 1.3863 | 0.097543
getJListPane | 2 | 0.69315 | 1.011
getModifyAction | 6 | 1.7918 | 0.0086762
getReadWriteModifyMode | 6 | 1.7918 | 0.0086762
getSingleNumberInput | 14 | 2.6391 | 0.88444
getNumbersInput | 6 | 1.7918 | 0.0086762
getQuantityOfNumbers | 11 | 2.3979 | 0.489
getFileLocation | 12 | 2.4849 | 0.61826
initializeAndDisplay | 25 | 3.2189 | 2.3112
initializeAndDisplayWithPrompt | 66 | 4.1897 | 6.2053
FileModeType | 5 | 1.6094 | 0.0079522
toString | 1 | 0 | 2.8853
FileModifyType | 8 | 2.0794 | 0.14503
toString | 1 | 0 | 2.8853
MyFileReader | 4 | 1.3863 | 0.097543
getFileContents | 6 | 1.7918 | 0.0086762
MyFileWriter | 4 | 1.3863 | 0.097543
setFileContents | 5 | 1.6094 | 0.0079522
Assignment 3B
Main | 46 | 3.8286 | 4.537
MainFrame | 1 | 0 | 2.8853
displayError | 2 | 0.69315 | 1.011
displayWarning | 5 | 1.6094 | 0.0079522
displayArrayList | 3 | 1.0986 | 0.36
getJListAsArray | 4 | 1.3863 | 0.097543
displaySingleString | 4 | 1.3863 | 0.097543
getJListPane | 2 | 0.69315 | 1.011
getModifyAction | 6 | 1.7918 | 0.0086762
getReadWriteModifyMode | 6 | 1.7918 | 0.0086762
getSingleNumberInput | 14 | 2.6391 | 0.88444
getNumbersInput | 6 | 1.7918 | 0.0086762
getQuantityOfNumbers | 11 | 2.3979 | 0.489
getFileLocation | 12 | 2.4849 | 0.61826
initializeAndDisplay | 25 | 3.2189 | 2.3112
initializeAndDisplayWithPrompt | 66 | 4.1897 | 6.2053
FileModeType | 5 | 1.6094 | 0.0079522
toString | 1 | 0 | 2.8853
FileModifyType | 8 | 2.0794 | 0.14503
toString | 1 | 0 | 2.8853
MyFileReader | 4 | 1.3863 | 0.097543
getFileContents | 6 | 1.7918 | 0.0086762
MyFileWriter | 4 | 1.3863 | 0.097543
setFileContents | 5 | 1.6094 | 0.0079522
Assignment 4B
Main | 64 | 4.1589 | 6.0529
getFileLocation | 4 | 1.3863 | 0.097543
MainFrame | 1 | 0 | 2.8853
displayError | 2 | 0.69315 | 1.011
displayWarning | 5 | 1.6094 | 0.0079522
displayArrayList | 3 | 1.0986 | 0.36
getJListAsArray | 4 | 1.3863 | 0.097543
displaySingleString | 4 | 1.3863 | 0.097543
getJListPane | 2 | 0.69315 | 1.011
getModifyAction | 6 | 1.7918 | 0.0086762
getReadWriteModifyMode | 6 | 1.7918 | 0.0086762
getSingleNumberInput | 14 | 2.6391 | 0.88444
getNumbersInput | 6 | 1.7918 | 0.0086762
getQuantityOfNumbers | 11 | 2.3979 | 0.489
getFileLocation | 30 | 3.4012 | 2.8988
initializeAndDisplay | 25 | 3.2189 | 2.3112
initializeAndDisplayWithPrompt | 66 | 4.1897 | 6.2053
FileModeType | 5 | 1.6094 | 0.0079522
toString | 1 | 0 | 2.8853
FileModifyType | 8 | 2.0794 | 0.14503
toString | 1 | 0 | 2.8853
MyFileReader | 4 | 1.3863 | 0.097543
getFileContents | 6 | 1.7918 | 0.0086762
MyFileWriter | 4 | 1.3863 | 0.097543
setFileContents | 5 | 1.6094 | 0.0079522
Assignment 5B
Main | 80 | 4.382 | 7.2007
getFileLocation | 4 | 1.3863 | 0.097543
MainFrame | 1 | 0 | 2.8853
displayError | 2 | 0.69315 | 1.011
displayWarning | 5 | 1.6094 | 0.0079522
displayArrayList | 6 | 1.7918 | 0.0086762
displayArrayListSingleRow | 5 | 1.6094 | 0.0079522
getJListAsArrayList | 4 | 1.3863 | 0.097543
getJListAsArrayListOfArrayList | 9 | 2.1972 | 0.24861
displaySingleRow | 1 | 0 | 2.8853
removeSingleRow | 9 | 2.1972 | 0.24861
getJListPane | 2 | 0.69315 | 1.011
getModifyAction | 6 | 1.7918 | 0.0086762
getReadWriteModifyMode | 6 | 1.7918 | 0.0086762
getSingleNumberInput | 14 | 2.6391 | 0.88444
getNumbersInput | 6 | 1.7918 | 0.0086762
getQuantityOfNumbers | 11 | 2.3979 | 0.489
getFileLocation | 30 | 3.4012 | 2.8988
initializeAndDisplay | 25 | 3.2189 | 2.3112
initializeAndDisplayWithPrompt | 78 | 4.3567 | 7.0655
FileModeType | 5 | 1.6094 | 0.0079522
toString | 1 | 0 | 2.8853
FileModifyType | 8 | 2.0794 | 0.14503
toString | 1 | 0 | 2.8853
MyFileReader | 4 | 1.3863 | 0.097543
getFileContents | 7 | 1.9459 | 0.061156
MyFileWriter | 4 | 1.3863 | 0.097543
setFileContentsWithArray | 6 | 1.7918 | 0.0086762
setFileContentsWithList | 3 | 1.0986 | 0.36

## Size Estimate Regression
PSP Regression Example
Inputs are in yellow, data used to find beta1 are in turquoise;beta0 and beta1 are in lavendar
Program Number I | Estimated Object LOC, Xi | Actual New and Changed LOC, Yi | XiYi | Xi^2 | (Yi-b0-b1Xi)^2 | (Xi-Xavg)^2 | Yi^ 2
|  |  | 0 | 0 | 0.20628 | 2061.16 | 0
2A | 60 | 92 | 5520 | 3600 | 347.3781 | 213.16 | 8464
2B | 70 | 81 | 5670 | 4900 | 21.7585 | 605.16 | 6561
3B | 5 | 4 | 20 | 25 | 2.8804 | 1632.16 | 16
4B | 53 | 43 | 2279 | 2809 | 473.0642 | 57.76 | 1849
5B | 39 | 57 | 2223 | 1521 | 89.7513 | 40.96 | 3249
Sum | 227 | 277 | 15712 | 12855 | 935.0388 | 4610.36 | 20139
Average | 45.4 | 55.4
n | 5
Using equations 5.2, page 122 (or table A27, page 545)
Regression | beta1 | beta0 | r^2
| 1.2303 | -0.45418 | 0.80497 |  | For low R^2, Time Estimate Method 5C1 used
Actual LOC = beta0 + beta1*(Estimated LOC)
Current Program
Estimated LOC | 36
Predicted LOC | 43.8355 | is adjusted (N) on C39 and C55
Variance | 311.6796
Std Deviation | 17.6544
t | 1.2498
Range | 24.3623 | LOC
Upper Prediction Interval | 68.1978 | LOC
Lower Prediction Interval | 19.4732 | LOC
Prediction Interval Percent | 70%

## Time Estimate Regression
PSP Regression Example
Inputs are in yellow, data used to find beta1 are in turquoise;beta0 and beta1 are in lavendar
Program Number I | Estimated Object LOC, Xi | Actual Time (min), Yi | XiYi | Xi^2 | (Yi-b0-b1Xi)^2 | (Xi-Xavg)^2 | Yi^ 2
|  |  | 0 | 0 | 1054.4302 | 2061.16 | 0
2A | 60 | 406 | 24360 | 3600 | 748.988 | 213.16 | 164836
2B | 70 | 560 | 39200 | 4900 | 15295.3203 | 605.16 | 313600
3B | 5 | 132 | 660 | 25 | 4995.8478 | 1632.16 | 17424
4B | 53 | 195 | 10335 | 2809 | 20519.6971 | 57.76 | 38025
5B | 39 | 179 | 6981 | 1521 | 6158.5183 | 40.96 | 32041
|  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0
Sum | 227 | 1472 | 81536 | 12855 | 48772.8018 | 4610.36 | 565926
Average | 45.4 | 294.4
n | 5
Using equations 5.2, page 122 (or table A27, page 545)
Regression | beta1 | beta0 | r^2
| 5.7693 | 32.472 | 0.64005 |  | For low R^2, Time Estimate Method 5C1 used
Actual Time = beta0 + beta1*(Estimated LOC)
Current Program
Estimated LOC | 36
Predicted Time | 240.1682 | minutes
Variance | 16257.6006
Std Deviation | 127.5053
t | 1.2498
Range | 175.9513 | minutes
Upper Prediction Interval | 416.1195 | minutes
Lower Prediction Interval | 64.2169 | minutes
Prediction Interval Percent | 70%